## Template
Project Plan Template
Project Name: | [6 empty] | Timeline: | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: | [6 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[21 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  |  | □ □ □ □ □ | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Workstream: | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
[7 empty] | 1/1 | 1/8 | 1/15 | 1/22 | 1/29 | 2/5 | 2/12 | 2/19 | 2/26 | 3/5 | 3/12 | 3/19 | 3/26 | 4/2
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status | □ □ □ □ □ Week 1 1/1: Holiday Week; □ □ □ □ □ Week 7 2/12: Reminder; □ □ □ □ □ Week 10 3/5: Important Date; □ □ □ □ □ Week 11 3/12: Holiday Week
Step 1 | [6 empty] | □ □ □ □ □ Week 3 1/15: 2024-11-06
Step 2
Step 3
Step 4
Step 5
Step 6
Step 7
Step 8
Step 9
Step 10
Workstream:
Step |  | Owner | Stakeholders/ Consulted |  | Due | Status
Workstream:
Step |  | Owner | Stakeholders/ Consulted |  | Due | Status
©2025 The Management Center

## Sample KYR Campaign
Project Plan Template
Project Name: | [6 empty] | Timeline: | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: CARE will host ten information sessions for advocates, schools, and nonprofits around the state. Sessions will be 1 hour; virtual and in-person. The program will show public support for queer youth and facilitate information about the law's policy implications with advocates. | [6 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[21 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  |  | □ □ □ □ □ | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Andrew | Janelle | Gail | Kyung (Marketing and Comms) Sam (Programming) Marielena (Logistics) Tony (Engagement) | Chloe
Workstream: Communications | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
[7 empty] | 2/5 | 2/12 | 2/19 | 2/26 | 3/5 | 3/12 | 3/19 | 3/26 | 4/2 | 4/9 | 4/16 | 4/23 | 4/30 | 5/6
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status | Week 3 2/19: Holiday; Week 7 3/19: Reminder; Week 10 4/9: Important Date; Week 11 4/16: Holiday Week
Develop messaging strategy |  | Kyung |  | 2025-02-12 | 2025-02-28 | Working on it | Week 4 2/26: 2025-02-28
Create branding materials |  | Kyung | Luis (social media) | 2025-03-05 | 2025-03-07 | Working on it | bar: Week 5 3/5
Design promotional materials |  | Kyung | Luis (social media) | 2025-03-07 | 2025-03-17 | bar: Week 5 3/5 to Week 6 3/12
Develop press release and media kit |  | Kyung | Didra, Coalition Table | 2025-03-14 | 2025-04-11 | bar: Week 6 3/12 to Week 10 4/9
Set up registration system (depends on XYZ) |  | Kyung | Carlota (Comms Ops) | 2025-03-23 | 2025-03-21 | bar: Week 6 3/12 to Week 7 3/19
Create social media campaign calendar |  | Kyung | Luis (social media) | 2025-03-22 | 2025-03-28 | bar: Week 7 3/19 to Week 8 3/26
Draft email communications template |  | Kyung |  | 2025-04-02 | 2025-04-04 | bar: Week 9 4/2
Create feedback surveys |  | Kyung |  | 2025-04-16 | 2025-04-18 | bar: Week 11 4/16
Workstream: Community Engagement | [6 empty] | 2/5 | 2/12 | 2/19 | 2/26 | 3/5 | 3/12 | 3/19 | 3/26 | 4/2 | 4/9 | 4/16 | 4/23 | 4/30 | 5/6
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
Identify target communities and organizations |  | Tony | Didra, Coaliton Table | 2025-02-12 | 2025-02-24 | Done | bar: 2/5 to 2/19
Create stakeholder database |  | Tony |  | 2025-02-23 | 2025-02-28 | Done | bar: 2/19 to 3/5
Develop outreach strategy |  | Tony | Didra, Coaliton Table | 2025-03-05 | 2025-03-07 | bar: 3/5
Create community feedback mechanisms |  | Tony |  | 2025-03-12 | 2025-04-18 | bar: 3/12 to 4/16
Schedule preliminary meetings with key partners |  | Tony |  | 2025-03-19 | 2025-03-24 | bar: 3/19 to 3/26
Train advocate volunteers |  | Tony | Sam | 2025-04-11 | 2025-04-11 | bar: 4/9
Establish ongoing communication channels |  | Tony | Kyung | 2025-04-17 | 2025-04-25 | bar: 4/16 to 4/23
Develop follow-up engagement plan |  | Tony | Coalition Table | 4/17 | 4/30 | bar: 4/16 to 4/30
Workstream: Logistics | [6 empty] | 2/5 | 2/12 | 2/19 | 2/26 | 3/5 | 3/12 | 3/19 | 3/26 | 4/2 | 4/9 | 4/16 | 4/23 | 4/30 | 5/6
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
Research venues |  | Marielena | Sam (programming) | 2025-02-14 | 2025-02-24 | Done | bar: 2/12 to 2/26
Create selection criteria for venues |  | Marielena |  | 2025-02-25 | 2025-02-27 | Stuck | bar: 2/26
Create budget for venues |  | Marielena | Hector (accounting) | 2/29 | 2025-02-26 | Working on it | bar: 2/26
Site visits |  | Marielena |  | 2025-02-26 | 2025-03-07 | Working on it | bar: 2/26 to 3/5
Plan setup and support needs |  | Marielena |  | 2025-03-07 | 2025-04-04 | bar: 3/5 to 4/2
Andrew reviews and approves selection criteria |  | Marielena | Andrew | 2025-03-12 | 2025-03-12 | bar: 3/12
Review Meeting: Compare venue options |  | Marielena |  | 2025-03-20 | 2025-03-21 | bar: 3/19
Book venues |  | Marielena |  | 2025-03-21 | 2025-03-21 | bar: 3/19
Confirm venue payment/processing with Finance |  | Marielena | Hector (accounting) | 2025-03-21 | 2025-03-28 | bar: 3/19 to 3/26
©2025 The Management Center